## TeamF
The Quarantwenties
| Contact Info |  | Introduction |  |  |  |  | Tic-Tac-Toe Game | [10 empty] | Sprint 1 |  |  |  |  | Sprint 2 | [5 empty] | Sprint 3 | [6 empty] | Sprint 4
Name | Email | Phone number | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-15
Chariane Nkengfack | cnkeng@student.fdu.edu | 908-305-0615 | bar: 2020-08-23 to 2020-09-29
Robert Vargas | r_vargas@student.fdu.edu | 908-405-0762 | bar: 2020-08-23 to 2020-09-29
Ever Nolasco | 1nolasco@student.fdu.edu | 908-220-2437 | bar: 2020-08-23 to 2020-09-29
Christina Schembri | cls18@student.fdu.edu | 347-510-1975 | 2020-08-23: x; 2020-08-24: Work; 2020-08-25: x; 2020-08-31: x; 2020-09-01: x; 2020-09-06: x; 2020-09-07: x; 2020-09-08: x; 2020-09-14: x; 2020-09-15: x; 2020-09-21: x; 2020-09-22: x; 2020-09-28: x
Michael DelSignore | mdel@student.fdu.edu | 973-413-4172 | bar: 2020-08-23 to 2020-09-29
Michael Elijius | elijiusm@student.fdu.edu | 862-223-1374 | bar: 2020-08-23 to 2020-09-29
Dominic Rzepecki | domrzep@student.fdu.edu | 973-407-0178 | 2020-08-23: x; 2020-08-24: Work; 2020-08-25: x; 2020-08-30: x; 2020-08-31: Work; 2020-09-01: x; 2020-09-06: x; 2020-09-07: x; 2020-09-08: x; 2020-09-13: x; 2020-09-15: x; 2020-09-20: x; 2020-09-22: x; 2020-09-27: x; 2020-09-29: x
Objectives/Agenda |  |  | 2020-08-23: Discuss team roles and the adjustments that will be made to them.; 2020-08-24: N/A; 2020-08-25: Make sure everyone has access to the Jira board, complete some of the homework as a group, and answer any questions the team may have.; 2020-08-30: Have everyone contribute to Jira project to show they have access to the Boards; 2020-08-31: Repeat of yesterday's meeting for those who couldn't attend; 2020-09-01: Discuss Tic-Tac-Toe game: planning, roles, timeline; 2020-09-04: N/A; 2020-09-05: N/A; 2020-09-06: Discuss team Kanban board and what acceptance criteria we need to meet for the issues/tasks in order to mark them as "Done."; 2020-09-07: Discuss the team retrospective and go over any last-minute issues regarding Jira & GitHub project.; 2020-09-08: Get feedback from Professor Vallone.; 2020-09-13: 1 -> Retro Revision (decide who's presenting which slide, summarize the slides and make it less wordy) 2 -> Prof. Vallone's feedback (status update from Ever: did you create Jira issues for it?) 3 -> Reminder for everyone to go over the tic-tac-toe implementation project Prof. Vallone sent us; 2020-09-14: Recap of yesterday's meeting.; 2020-09-15: Revise the Tic-Tac-Toe retro as a team.; 2020-09-20: Establish Team Coding Guidelines.; 2020-09-21: Revise the Coding Standards & Guidelines document.; 2020-09-22: Go over Timeline, Tools doc, and Requirements doc; 2020-09-27: Address progress of Jira board, and complete daily stand-up.; 2020-09-28: Address progress of Jira board, and complete daily stand-up.; 2020-09-29: Discussed roles and status of game, and went through daily stand-up.
Meeting details/notes |  |  | 2020-08-23: Chariane mentioned that she's going to have to move around the team roles based on Prof. Vallone's helpful suggestions. She also wanted to ensure that her teammates were satisfied with their role assignments. Michael E brought up a great point of asking the team to clarify what each role meant and what their responsibilities & expectations encompassed. This question will be re-addressed during class tomorrow (08/25) to Prof. Vallone for further clarification.; 2020-08-24: Chariane made sure everyone was comfortable with the new team role assignments. Short meeting.; 2020-08-25: Discussed team norms, accessed team project on Jira, and organized team retrospective presentation slide.; 2020-08-30: Everyone agreed to learn Git and also make some edits/comments/issues in the Jira project to show that they have access to it.; 2020-08-31: Everyone agreed to learn Git and also make some edits/comments/issues in the Jira project to show that they have access to it.; 2020-09-01: We discussed how everyone's roles will affect the production, planning, and execution of this game, and we also created a timeline for when we should expect certain components to be done.; 2020-09-04: We tried to fix some GitHub branching issues, and we made it a learning experience regarding pull requests, cloning/forking, and merging.; 2020-09-05: We ran into some merging issues and one of the two project configurations (the multiplayer one) is not working for some reason.; 2020-09-06: We went through each of our open issues/bugs and discussed what acceptance critiera was missing in order to declare he item as "Done," we made sure every team member was able to "Pull from Origin" using GitHub desktop to ensure that they had the most up-to-date repo on their system, and we helped our team members open and run the newest game on their computers from the correct branch.; 2020-09-07: We came up with some bullet points for our team retro, and we tried to troublesheet an issue with the Visual Studio project files. It was throwing out random errors that we didn't encounter after yesterday's smooth merge, so we sorted this issue out as a team.; 2020-09-08: Professor Vallone provided the team with some insightful feedback regarding our coding methods, GitHub repo, and our overrall project execution skillset.; 2020-09-13: 1 -> Retro slide is finished and speaking points are assigned 2 -> Updates unknown; Ever not in meeting 3 -> Will do after meeting; 2020-09-14: Made sure everyone was aware of the changes to the Retro slide, and that they were prepped for today's presentation.; 2020-09-15: We added additional bullets to each section and we assigned speaking points for each teammate.; 2020-09-20: We explored different ideas and came up with a brief document, outlining our team's coding standards and guidelines. We plan to apply these guidelines to all of our future coding projects.; 2020-09-21: We added more items to our team doc and updated it in the repo.; 2020-09-22: We created a project timeline, revisited our Tools document, and created our Project Requirements.; 2020-09-27: Completed our stand-up and ensured that everyone will update and close out their tasks on the Scrum board.; 2020-09-28: Completed our stand-up and ensured that everyone will update and close out their tasks on the Scrum board.; 2020-09-29: We nominated Dominic as the Product Owner and we identified some goals we wanted to meet before presenting the game to the class next Monday.
Action Items |  |  | 2020-08-23: Readdress definition of team roles during class.; 2020-08-24: N/A; 2020-08-25: Chariane will finish the assigned homework items and submit them on Jira.; 2020-08-30: Everyone is going to make a comment or create an issue to show that they have access to the Jira project, if they haven't done so already.; 2020-08-31: N/A; 2020-09-01: Chariane and Christina will work on Tools doc, Dominic will create living doc for Requirements, Ever and Michael E. will code, and Michael D. and Rob will test the program.; 2020-09-04: Michael E is going to try to combine the two tic-tac-toe projects into one.; 2020-09-05: Ever is going to try to combine the two projects into one.; 2020-09-06: Group will come up with bullet points for team retrospective during tomorrow's meeting. Rob will test the program and report any additionl bugs to the coders.; 2020-09-07: N/A; 2020-09-08: We will review the team retro during next Sunday's meeting and add anything else that comes to mind.; 2020-09-13: N/A; 2020-09-14: N/A; 2020-09-15: N/A; 2020-09-20: Everyone must come up with at least 3 additional items for Coding Standards & Guidelines doc for tomorrow's meeting.; 2020-09-21: N/A; 2020-09-22: Get the Jira workspace set up.; 2020-09-27: Complete your Jira issues.; 2020-09-28: Complete your Jira issues.; 2020-09-29: Have coders close out their Jira tasks and expand upon the gameplay before next class.
Meeting length (in minutes) |  |  | 2020-08-23: 15; 2020-08-24: 3; 2020-08-25: 30; 2020-08-30: 5; 2020-08-31: 5; 2020-09-01: 28; 2020-09-04: 30; 2020-09-05: 30; 2020-09-06: 17; 2020-09-07: 50; 2020-09-08: 55; 2020-09-13: 30; 2020-09-14: 5; 2020-09-15: 20; 2020-09-20: 35; 2020-09-21: 17; 2020-09-22: 50; 2020-09-27: 5; 2020-09-28: 20; 2020-09-29: 10
Key:
scrum meetings
optional/spontaneous meetings
missing
couldn't attened but told the team and sent a progress update
couldn't attend optional/spontaneous meetings